## Action Plan Template
Step #1: Initial Research |  |  |  |  | Timeline |  | Resources
Priority | Task (Action Item) | Phase | Assigned | Start Date | Due Date | Planned Hours | Department | Materials Required | Status | Notes
Low | AC-2 | Planning | Joshua | 2021-10-28 | 2021-12-06 | 3-5 Days | Databased Admin | Account Management | 0% | Additon of milestrones
High | AC-7 | Planning | Joshua | 2021-10-28 | 2021-12-06 | 7-10 Days | Databased Admin | Unsuccesful Logn Attempts | 25%
Medium | AC-8 | Planning | Joshua | 2021-10-28 | 2021-12-06 | 5-7 Days | Databased Admin | System Use Notifcation | 0%
Low | AT-4 | Planning | Joshua | 2021-10-28 | 2021-12-06 | 1-3 Days | Database Manager | Security Training Records | 50%
Step #2: Launching |  |  |  |  | Timeline |  | Resources
Priority | Task (Action Item) | Phase | Assigned | Start Date | Due Date | Planned Hours | Department | Materials Required | Status | Notes
Low | AC-2 | Execution | Joshua | 2021-10-28 | 2021-12-06 | 3-5 Days | Databased Admin | Account Management | 100% | Policy successfully completed and implemented
High | AC-7 | Execution | Joshua | 2021-10-28 | 2021-12-06 | 7-10 Days | Databased Admin | Unsuccesful Logn Attempts | 40% | Number of locking attemps detemriend by company policy
Medium | AC-8 | Execution | Joshua | 2021-10-28 | 2021-12-06 | 5-7 Days | Databased Admin | System Use Notifcation | 50% | Notifications being done outside of MySQL
Low | AT-4 | Execution | Joshua | 2021-10-28 | 2021-12-06 | 1-3 Days | Database Manager | Security Training Records | 100% | Policy successfully completed and implemented